| Sustainability project – Minutes meeting 1 |  |  |
| --- | --- | --- |
| Date: 04/04/2018 |  | Venue: online meeting (Skype) |
| Start: 14:15 pm | End: 14:55 |  |

| Present | Brecht Polley, Pieter Segaert, Maarten Van Goethem, Ruben Van Renterghem, Oliver vileyn |
| --- | --- |
| Absent | /// |
| Chairs | Maarten Van Goethem |
| Secretaries | Brecht |

Agenda:

• Briefing

• Divide the workload

• Deadline

• Peer assessment

Minutes:

- Repeat what was said last meeting to those who were absent.

- division of the workload + agreed on the deadlines

18th of April:

Maarten: work breakdown of the project

Ruben: design a logo

Oliver: mail school about the possibility to use the Kantine and the possibility to

sell the left-overs, mail to the city of Ghent for the use of traditional games

Brecht: create a slogan and find sponsors

Pieter: make a scenario (who does what on the day itself)

22nd of April: financial plan, poster

25th of April: finish the PowerPoint

Date of the Dinner: Wednesday 9th may: 18:30 – 20:00

Don’t forget the peer assessment due to 6th of April 10 PM

Next meeting: 15/04